## High Level Plan
High Level Planning / Activities of Healthcare DW / Data Lake Project
2024-05-24
2nd - 10th | 13th-17th | 20th-24th | 27th-31st
Data Dicitonary | ETL Architecture | Dimensional Modeling | Completion of Dimensional Modeling
AWS Infra Requirement | AWS Python Installaion & EC2 | ETL Sample Data Flow | Data Existance and Managing Data in Staging and Production
Data Access | Beginning of Dimensional Model | Code Repository | SSRS Reporting Requirement
Beginning of Conceptual Model | BRD for PowerBI Reports (Users and KPI) | BRD Documentation | PowerBI Reporting Requirement
Data Analysis | AWS Required Services Up and Running | Promax and Ace Data Understanding | Development of ETL Jobs
| Review from Joseph and Team |  | Review from Joseph and Team
2024-06-24
3rd - 7th | 10th-14th | 17th-21st | 24th-28th
Data extraction and Retention Stratagy | ETL Development | Data population in one star schema | SSRS Reporting Development
SSRS Development Server | BRD Final on PowerBI Requirements | PowerBI Report Development | PowerBI Report Development
ETL Development | Population of Dimension Tables | SSRS Pre Development Stage | Building Data Population (ETL)
BRD Last Stage | Validating the Star Schema with Source | Automation of Data Pipeline POC | How many years of Data we should have in DW?
| Review from Joseph and Team |  | Review from Joseph and Team
2024-07-24
1st-5th | 8th-12th | 15th-19 | 22nd-31st
Data Validation & Reconciliation | Data Validation & Reconciliation | Role definition of PowerBI Reports | Preparation for Production DB's
SSRS Development | SSRS Development | PowerBI Development | PowerBI Testing
PowerBI Development | PowerBI Development | Validation of ETL | SSRS Tetsing
Finalizing Data Population | Validation first set of Reports | Preparation for Production ETL | ETL Testing
| Review from Joseph and Team |  | Review from Joseph and Team
2024-08-24
1st - 9th | 12th - 16th | 19th-23rd | 26th - 30th
Migration Scripts on Python | Supporting the live | ETL & BI Support | ETL & BI Support
Migration Scripts on DB | PowerBI Validation
Final QA | ETL Validation
Go Live | SSRS Validation
Review from Joseph and Team | Review from Joseph and Team |  | Review from Joseph and Team on Stabilization
2024-08-24
One Developer Supporting the entire Application